## Sheet1
Test Case | Use Case | Function Being Tested | Initial System State | Input | Expected Output | Actual Output (v1.0) | Actual Output (v1.1) - Regression | Notes | Bug Link
1 | System Startup | System is started when the switch is turned "on" | System is off | Activate the "on" switch | System requests initial cash amount | Output displayed as expected | Output displayed as expected | No bug | NA
2 | System Startup | System accepts initial cash amount | System is requesting cash amount | Enter a legitimate amount | System is on | Entering any valid integer greater than 2147483647 doesn't get accepted | Entering any valid integer greater than 2147483647 doesn't get accepted | Bug found by scripted testing | https://seng637g5.backlog.com/view/ATM_1-8
3 | System Startup | Connection to the bank is established | System has just been turned on | Perform a legitimate inquiry transaction | System output should demonstrate that a connection has been established to the Bank | No log for startup showing Connection to the bank is established | No log for startup showing Connection to the bank is established | Bug found by scripted testing | https://seng637g5.backlog.com/view/ATM_1-24
4 | System Shutdown | System is shut down when the switch is turned “off" | System is on and not servicing a customer | Activate the "off" switch | System is off | Output displayed as expected | Output displayed as expected | No bug | NA
5 | Session | System reads a customer's ATM card | System is on and not servicing a customer | Insert a readable card | Card is accepted; System asks for entry of PIN | Output displayed as expected | Output displayed as expected | No bug | NA
6 | Session | System rejects an unreadable card | System is on and not servicing a customer | Insert an unreadable card | Card is ejected; System displays an error screen; System is ready to start a new session | System still asks for pin with invalid card | System still asks for pin with invalid card | Bug found during exploratory testing as well. | Not yet logged
7 | Session | System accepts customer's PIN | System is asking for entry of PIN | Enter a PIN | System displays a menu of transaction types | Output displayed as expected | Output displayed as expected | No bug | NA
8 | Session | System allows customer to perform a transaction | System is displaying menu of transaction types | Perform a transaction | System asks whether customer wants another transaction | Output displayed as expected | Output displayed as expected | No bug | NA
9 | Session | System allows multiple transactions in one session | System is asking whether customer wants another transaction | Answer yes | System displays a menu of transaction types | Output displayed as expected | Output displayed as expected | No bug | NA
10 | Session | Session ends when customer chooses not to do another transaction | System is asking whether customer wants another transaction | Answer no | System ejects card and is ready to start a new session | Output displayed as expected | Output displayed as expected | No bug | NA
11 | Transaction | System handles an invalid PIN properly | A readable card has been entered | Enter an incorrect PIN and then attempt a transaction | The Invalid PIN exception is performed | Output displayed as expected | Output displayed as expected | No bug | NA
12 | Withdrawal | System asks customer to choose an account to withdraw from | Menu of transaction types is being displayed | Choose Withdrawal transaction | System displays a menu of account types | Output displayed as expected | Output displayed as expected | No bug | NA
13 | Withdrawal | System asks customer to choose a dollar amount to withdraw | Menu of account types is being displayed | Choose checking account | System displays a menu of possible withdrawal amounts | Output displayed as expected | The third option is missing dollar sign for 60. | Bug found during exploratory testing as well. | Not yet logged
14 | Withdrawal | System performs a legitimate withdrawal transaction properly | System is displaying the menu of withdrawal amounts | Choose an amount that the system currently has and which is not greater than the account balance | System dispenses this amount of cash; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) | You choose withdraw $60, but ATM dispenses $100. You choose to withdraw $200, but ATM dispenses $20. This happens incorrectly for every amount. | Output displayed as expected | Bug found by scripted testing | https://seng637g5.backlog.com/view/ATM_1-14
15 | Withdrawal | System verifies that it has sufficient cash on hand to fulfill the request | System has been started up with less than the maximum withdrawal amount in cash on hand; System is requesting a withdrawal amount | Choose an amount greater than what the system currently has | System displays an appropriate message and asks customer to choose a different amount | Output displayed as expected | Output displayed as expected | No bug | NA
16 | Withdrawal | System verifies that customer's balance is sufficient to fulfill the request | System is requesting a withdrawal amount | Choose an amount that the system currently has but which is greater than the account balance | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected. However during input, the bug in #14 has to be kept in mind. | Output displayed as expected | No bug | NA
17 | Withdrawal | A withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount | System is displaying menu of account types | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
18 | Withdrawal | A withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount | System is displaying menu of dollar amounts | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
19 | Deposit | System asks customer to choose an account to deposit to | Menu of transaction types is being displayed | Choose Deposit transaction | System displays a menu of account types | Output displayed as expected | Output displayed as expected | No bug | NA
20 | Deposit | System asks customer to enter a dollar amount to deposit | Menu of account types is being displayed | Choose checking account | System displays a request for the customer to type a dollar amount | Output displayed as expected | Output displayed as expected | No bug | NA
21 | Deposit | System asks customer to insert an envelope | System is displaying a request for the customer to type a dollar amount | Enter a legitimate dollar amount | System requests that customer insert an envelope | Output displayed as expected | Output displayed as expected | No bug | NA
22 | Deposit | System performs a legitimate deposit transaction properly | System is requesting that customer insert an envelope | Insert an envelope | System accepts envelope; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing message to the bank, approval back, and acceptance of the envelope) | BUG: $100 inserted but only $90 got reflected in both checking and money market accounts | BUG: $100 inserted but only $99.9 got reflected in both checking and money market accounts | Bug found during exploratory testing as well. | https://seng637g5.backlog.com/view/ATM_1-22
23 | Deposit | A deposit transaction can be cancelled by the customer any time prior to inserting an envelope | System is displaying menu of account types | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
24 | Deposit | A deposit transaction can be cancelled by the customer any time prior to inserting an envelope | System is requesting customer to enter a dollar amount | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
25 | Deposit | A deposit transaction can be cancelled by the customer any time prior to inserting an envelope | System is requesting customer to insert an envelope | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
26 | Transfer | System asks customer to choose an account to transfer from | Menu of transaction types is being displayed | Choose Transfer transaction | System displays a menu of account types specifying transfer from | Output displayed as expected | Output displayed as expected | No bug | NA
27 | Transfer | System asks customer to choose an account to transfer to | Menu of account types to transfer from is being displayed | Choose checking account | System displays a menu of account types specifying transfer to | Output displayed as expected | Output displayed as expected | No bug | NA
28 | Transfer | System asks customer to enter a dollar amount to transfer | Menu of account types to transfer to is being displayed | Choose savings account | System displays a request for the customer to type a dollar amount | Output displayed as expected (although card #2 has no Savings account) | Output displayed as expected (although card #2 has no Savings account) | No bug | NA
29 | Transfer | System performs a legitimate transfer transaction properly | System is displaying a request for the customer to type a dollar amount | Enter a legitimate dollar amount | System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) | The amount transferred is $0.5 less. FROM and TO are reversed in the receipt | FROM and TO are reversed in the receipt | Bug found during exploratory testing as well. | https://seng637g5.backlog.com/view/ATM_1-15
30 | Transfer | A transfer transaction can be cancelled by the customer any time prior to entering dollar amount | System is displaying menu of account types specifying transfer from | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
31 | Transfer | A transfer transaction can be cancelled by the customer any time prior to entering dollar amount | System is displaying menu of account types specifying transfer to | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
32 | Transfer | A transfer transaction can be cancelled by the customer any time prior to entering dollar amount | System is requesting customer to enter a dollar amount | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
33 | Inquiry | System asks customer to choose an account to inquire about | Menu of transaction types is being displayed | Choose Inquiry transaction | System displays a menu of account types | Output displayed as expected | Output displayed as expected | No bug | NA
34 | Inquiry | System performs a legitimate inquiry transaction properly | System is displaying menu of account types | Choose checking account | System prints a correct receipt showing correct balance; System records transaction correctly in the log (showing both message to the bank and approval back) | Output displayed as expected | Output displayed as expected | No bug | NA
35 | Inquiry | An inquiry transaction can be cancelled by the customer any time prior to choosing an account | System is displaying menu of account types | Press "Cancel" key | System displays an appropriate message and offers customer the option of choosing to do another transaction or not. | Output displayed as expected | Output displayed as expected | No bug | NA
36 | Invalid PIN Extension | Customer is asked to reenter PIN | System is asking for entry of PIN | Enter an incorrect PIN; Attempt an inquiry transaction on the customer's checking account | Customer is asked to re-enter PIN | Output displayed as expected | Output displayed as expected | No bug | NA
37 | Invalid PIN Extension | Correct re-entry of PIN is accepted | Request to re-enter PIN is being displayed | Enter correct PIN | Original transaction completes successfully | ATM requests to enter correct PIN one more time | ATM requests to enter correct PIN one more time | Bug found during exploratory testing as well. | https://seng637g5.backlog.com/view/ATM_1-19
38 | Invalid PIN Extension | Incorrect re-entry of PIN is not accepted | Request to re-enter PIN is being displayed | Enter incorrect PIN | An appropriate message is displayed and re-entry of the PIN is again requested | Output displayed as expected | Output displayed as expected | No bug | NA
39 | Invalid PIN Extension | Correct re-entry of PIN on the second try is accepted | Request to re-enter PIN is being displayed | Enter incorrect PIN the first time, then correct PIN the second time | Original transaction completes successfully | On incorrect PIN, ATM requests to enter correct pin. Then on correct PIN, ATM requests to enter correct PIN one more time. | On incorrect PIN, ATM requests to enter correct pin. Then on correct PIN, ATM requests to enter correct PIN one more time. | Bug found during exploratory testing as well. | https://seng637g5.backlog.com/view/ATM_1-19
40 | Invalid PIN Extension | Correct re-entry of PIN on the third try is accepted | Request to re-enter PIN is being displayed | Enter incorrect PIN the first time and second times, then correct PIN the third time | Original transaction completes successfully | For each entry of incorrect PIN, ATM requests to enter correct PIN. Then finally on correct PIN, ATM requests to enter correct PIN one more time. | For each entry of incorrect PIN, ATM requests to enter correct PIN. Then finally on correct PIN, ATM requests to enter correct PIN one more time. | Bug found during exploratory testing as well. | https://seng637g5.backlog.com/view/ATM_1-19