## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3657688 | 68251 | ATM Project | 22 | ATM_1-22 | 292312 | Bug | 92644 | Deposit | 63901 | 1.0 | Deposit amount is incorrect | When a user deposits money, the amount deposited into account is less than the amount entered **Function being tested** : Deposit **Initial state of the system** : System is displaying a request for the customer to type a dollar amount **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 1 and enter the PIN as 42 3. Choose transaction type as Balance Inquiry 4. Choose any valid account (Checking used in this case) 5. Enter amount 6. Insert envelope **Version 1.0** **Expected Outcome** : The amount deposited is the same as the amount entered. The receipt should show the initial balance plus the deposited amount. Performing a balance inquiry following this should show this new balance. **Actual Outcome** : The amount deposited is $10 less than the amount entered. The receipt shows the initial balance plus the deposited amount less $10. Performing a balance inquiry shows same balance as receipt from the deposit (short $10) **UPDATE** **Version 1.1** **Expected Outcome** : The amount deposited is the same as the amount entered. The receipt should show the initial balance plus the deposited amount. Performing a balance inquiry following this should show this new balance. **Actual Outcome** : The amount deposited is $0.10 less than the amount entered. The receipt shows the initial balance plus the deposited amount less $0.10. Performing a balance inquiry shows same balance as receipt from the deposit (short $0.10) ![image][Issue_22.jpg] | 2 | In Progress | 3 | Normal | [6 empty] | 319598 | Drew Burritt | Jan. 28, 2022 22:10 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 15:19 | 1 | 0 | Jan. 30, 2022 14:37 Bhavyai Gupta Defect still exists in version 1.1
3657850 | 68251 | ATM Project | 23 | ATM_1-23 | 292312 | Bug | 92647 | Session | 63901 | 1.0 | ATM erratically dispenses a $20 bill | ![image][Blank diagram (3).jpeg] During any option selection session, if the user enters a number selection higher than the highest number available , the ATM dispenses a $20 bill. This dispensation is captured in the log, but the account balance is not affected. **Function being tested:** Session **Initial state of the system:** After any transaction, the System prompts the user "Wood you like to do another transaction?". **Steps to reproduce:** 1. Turn ON ATM and enter a valid number of bills. 2. Insert a valid card, and enter correct PIN. 3. When promoted with a numbered selection of operations to perform, Enter any number higher that the last selection ( "4. Balance Inquiry"), let's say "5". OR 1. Perform an Inquiry transaction. 2. When prompted "Would you like to do another transaction?", Enter any number other than 1 or 2. **Expected outcome:** A Failure Message saying "Invalid selection". **Actual outcome:** The ATM dispenses a $20 bill. This dispensation is captured in the log, but the account balance is not affected. | 2 | In Progress | 3 | Normal | [6 empty] | 319596 | OKEOGHENEMARHO OBUAREGHE | Jan. 29, 2022 00:51 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 15:06 | 1 | 0 | Jan. 29, 2022 00:55 OKEOGHENEMARHO OBUAREGHE Fixed in V1.1 | Jan. 30, 2022 15:06 Bhavyai Gupta Defect still exists in version 1.1. This bug is partially fixed. In v1.0, $20 were dispensed when any number other than the highest valid option is selected. For example, if menu lists valid options 1, 2, and 3, then an input of any number 4 to 9 and 0 would dispense $20 bill. In v1.1, $20 are dispensed when the input is one higher than the highest valid option. For example, if menu lists valid options 1, 2, and 3, then an input of 4 would dispense $20 bill. The other inputs wont have any affect.
3657674 | 68251 | ATM Project | 21 | ATM_1-21 | 292312 | Bug | 92643,92644,92645,92646 | Withdrawal,Deposit,Transfer,Balance Inquiry | 63901 | 1.0 | Card number on receipt is incorrect | When a a receipt is printed after a transaction is finished, the card number shown on the receipt is one higher than the actual card number. (card #1 shows as card #2) **Function being tested** : Any Transaction **Initial state of the system** : System on any transaction screen ![image][bug.jpg] **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 1 and enter the PIN as 42, or card 2 pin 1234 3. Choose any transaction type 4. Choose any valid option for the selected transaction type. **Expected Outcome** : The receipt should be should show the card number used. Ie. #1 for card #1, #2 for card #2 **Actual Outcome** :The receipt shows the card number as one higher than the actual card number . Ie. #2 for card #1, #3 for card #2 The card number shown in ATM log is correct, it is just the receipt. | 2 | In Progress | 3 | Normal | [6 empty] | 319598 | Drew Burritt | Jan. 28, 2022 21:46 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 14:37 | 1 | 0 | Jan. 30, 2022 14:37 Bhavyai Gupta Defect still exists in version 1.1
3657582 | 68251 | ATM Project | 19 | ATM_1-19 | 292312 | Bug | 92647 | Session | 63901 | 1.0 | Correct PIN has to be entered twice | Anytime a wrong PIN is entered, it take the two consecutive attempts of entering the correct PIN before the ATM proceeds to access the card. **Function being tested:** Session **Initial state of the system:** System has just been turned ON. **Steps to reproduce:** 1. Turn ON ATM, and insert valid number of bills. 2. Insert a Card, and enter an incorrect PIN. 3. Machine reads "PIN was incorrect, Please re-enter your PIN". 4. Enter correct PIN. 5. Machine prompts user to enter PIN again. ![image][Blank diagram.jpeg] **Expected outcome:** ATM should grant access to card once the correct PIN has been entered. **Actual outcome:** ATM request for the correct PIN for a second time before granting access to card. | 2 | In Progress | 3 | Normal | [6 empty] | 319596 | OKEOGHENEMARHO OBUAREGHE | Jan. 28, 2022 19:31 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 14:31 | 1 | 0 | Jan. 30, 2022 14:31 Bhavyai Gupta Defect still exists in version 1.1
3657557 | 68251 | ATM Project | 18 | ATM_1-18 | 292312 | Bug | 92647 | Session | 63901 | 1.0 | No limit on PIN length | No limit on PIN length; any large number causes the GUI to freeze and java.lang.NumberFormatException is thrown on the command line. **Function being tested:** Session **Initial state of the system:** System has just been turned ON. **Steps to reproduce:** 1. Turn on ATM, and insert valid number of bills. 2. Insert a Card, and enter a long value for PIN. **Expected outcome:** A Failure Message saying "Invalid Card/PIN". **Actual outcome:** The GUI freezes, and java.lang.NumberFormatException is thrown on the command line. ![image][MFT 2.JPG] | 2 | In Progress | 3 | Normal | [6 empty] | 319596 | OKEOGHENEMARHO OBUAREGHE | Jan. 28, 2022 19:01 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 14:30 | 1 | 0 | Jan. 30, 2022 14:30 Bhavyai Gupta Defect still exists in version 1.1
3654832 | 68251 | ATM Project | 15 | ATM_1-15 | 292312 | Bug | 92645 | Transfer | 63901 | 1.0 | FROM and TO are reversed in the transfer receipt. | **Function being tested** : Transfer **Initial State of the system** : User Withdrawal from menu and choose $60. **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 1 and enter the PIN as 42 3. Choose Transfer 4. Choose Savings for From 5. Choose Checking for To 6. Enter $1.00 as amount **Expected Outcome** ATM receipt shows from savings to checking of $1.00 **Actual Outcome** ATM receipt shows from checking to savings of $0.50 ![image][pasted-2022.01.27-15.36.23.png] | 2 | In Progress | 3 | Normal | [6 empty] | 319500 | Michael Lee | Jan. 27, 2022 15:37 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 14:29 | 1 | 0 | Jan. 30, 2022 14:29 Bhavyai Gupta Defect still exists in version 1.1
3654813 | 68251 | ATM Project | 12 | ATM_1-12 | 292312 | Bug | 92644 | Deposit | 63901 | 1.0 | ATM doesn't accept a big deposit amount | Whenever we try to deposit an amount greater than 21474836.47, the ATM screen becomes non-responsive and `java.lang.NumberFormatException` is thrown on the command line console. FYI, the figure mentioned is not even the 32-bit int limit. **Function being tested** : Deposit **Initial state of the system** : ATM is requesting to enter the amount to deposit **Steps to reproduce** : 1. Insert the card 2 and enter the PIN as 1234 2. Choose transaction type as Deposit, and then choose checking account 3. Key in 21474836.48 as the deposit amount and press Enter. 4. You will see that the ATM doesn't show any button to enter the envelope. ATM's screen has also gone blank and does not respond to any of the buttons. There is nothing in the logs. 5. Open the console that you used to launch the jar file. You'll see the `java.lang.NumberFormatException` exception there. **Expected Outcome** : ATM should have asked to enter the envelope and proceeded with the deposit of entered amount. **Actual Outcome** : The ATM didn't ask to enter the envelope. Its screen is also blank and not responding to any of the buttons. ![image][Issue_12_Screenshot.png] | 2 | In Progress | 3 | Normal | [6 empty] | 319606 | Bhavyai Gupta | Jan. 27, 2022 15:12 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 11:42 | 1 | 0 | Jan. 30, 2022 11:42 Bhavyai Gupta Defect still exists in version 1.1
3651665 | 68251 | ATM Project | 8 | ATM_1-8 | 292312 | Bug | 92647 | Session | 63901 | 1.0 | ATM doesn't accept large number of bills in the cash dispenser | **MFT** After starting the ATM, we need to enter number of $20 bills that the ATM has in its cash dispenser. Entering any valid integer greater than 2147483647 doesn't get accepted. FYI, this value is equal to 2^31 - 1. **Function being tested** : Session **Initial state of the system** : OFF **Steps to reproduce** : 1. Click the ON button to turn ATM on. 2. Enter any integer that is greater than 2147483647. For example, enter 2147483648. 3. ATM will show message - "Must be a valid integer >= 0". The number that we had entered is a valid integer greater than or equal to 0. So it should have been accepted by the ATM **Expected Outcome** : The ATM should have accepted the number 2147483648 as the number of $20 bills present in the cash dispenser. **Actual Outcome** : The ATM doesn't accept 2147483648 and shows the message "Must be a valid integer >= 0". ![image][Issue_Screenshot.png] | 2 | In Progress | 3 | Normal | [6 empty] | 319606 | Bhavyai Gupta | Jan. 26, 2022 15:48 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 11:42 | 1 | 0 | Jan. 30, 2022 11:42 Bhavyai Gupta Defect still exists in version 1.1
3652315 | 68251 | ATM Project | 10 | ATM_1-10 | 292312 | Bug | 92645 | Transfer | 63901 | 1.0 | ATM allows to transfer more than the account balance | The ATM allows to transfer more than the total balance. After such a transfer, the total balance starts showing invalid numerical figures. **Function being tested** : Transfer **Initial state of the system** : ON and Idle **Steps to reproduce** : 1. Insert the card 1 and enter the PIN as 42 2. Choose transaction type as Deposit, and make a deposit of $0.00 in the checking account. Due to another bug, $10 will be deducted making it Total Balance equal to $90.00 3. Press 1 to do another transaction 4. Now choose transaction type as Transfer. 5. Select from "Checking" and to "Savings" 6. Enter $100.00 as the amount to transfer, and press Enter. Due to bug [ATM_1-9](https://seng637g5.backlog.com/view/ATM_1-9), $99.50 will be transferred from "Checking" to "Savings" account. 7. Press 1 to do another transaction 8. Choose transaction type as Balance Inquiry 9. Select "Checking" account 10. Total balance will be shown as $-9.0-50, which isn't even a valid number **Expected Outcome** : In version 1.0, the ATM shouldn't allow the transfer as the total balance of $90.00 is less than the amount being transferred, which is $100.00. **Actual Outcome** : The ATM allows to transfer more than the total balance present in the checking account. Also, the final figure shown in the balance inquiry is not a valid numeral. ![image][Issue_Screenshot.png] | 2 | In Progress | 3 | Normal | [6 empty] | 319606 | Bhavyai Gupta | Jan. 26, 2022 21:20 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 11:41 | 1 | 0 | Jan. 30, 2022 11:41 Bhavyai Gupta Defect still exists in version 1.1, except that the output will be slightly different. Screenshots of both version are included in the original attached image. **Expected Outcome** : In version 1.1 the ATM shouldn't allow the transfer as the total balance of $99.90 is less than the amount being transferred, which is $100.00. **Actual Outcome** : The ATM allows to transfer more than the total balance present in the checking account. Also, the final figure shown in the balance inquiry is not a valid numeral. ![image][Issue_Screenshot.png]
3657662 | 68251 | ATM Project | 20 | ATM_1-20 | 292312 | Bug | 92647 | Session | 63901 | 1.0 | The word transaction can appear truncated on some systems | Whenever a user completes a transaction, he would get a message to respond to - "Would you like to do another transaction?". The issue is that this message is truncated depending upon the users display resolution and scaling. **Function being tested** : Session **Initial state of the system** : System completes any transaction successfully **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 1 and enter the PIN as 42 3. Choose transaction type as Balance Inquiry 4. Choose account as Checking 5. Now you won't see the full message as it is truncated 6. You can also repeat the above steps 1 to 5, after you have decrease the scaling. Depending on your system, you might be able to see the full message. **Expected Outcome** : The message should be wrapped on the available screen rather than getting truncated. **Actual Outcome** : The message got truncated and a part of it is not visible. ![image][Issue_20_Screenshot.png] | 2 | In Progress | 4 | Low | [6 empty] | 319606 | Bhavyai Gupta | Jan. 28, 2022 21:32 |  | 319606 | Bhavyai Gupta | Jan. 30, 2022 11:39 | 1 | 0 | Jan. 30, 2022 11:39 Bhavyai Gupta Defect still exists in version 1.1
3651268 | 68251 | ATM Project | 4 | ATM_1-4 | 292312 | Bug | 92647 | Session | 63901 | 1.0 | Typo "Wood" in message | After completing any transaction, the ATM prompts the user with a message “Wood you like to do another transaction”; in this message, “Wood” is supposed to be spelled “Would”. **Function being tested** : Session **Initial state of the system** : System completes any transaction successfully. **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 2 and enter the PIN as 1234 3. Choose transaction type as Balance Inquiry 4. Choose account as Checking (Misspelled word would show after action is completed) **Expected Outcome** ATM displays “Would you like to do another transaction? **Actual Outcome** ATM shows “Wood you like to do another transactio”. ![image][pasted-2022.01.26-09.35.46.png] | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed |  |  | 319500 | Michael Lee | Jan. 26, 2022 09:36 |  | 319606 | Bhavyai Gupta | Jan. 28, 2022 21:20 | 1 | 0 | Jan. 26, 2022 09:40 Michael Lee Typo fixed in version 1.1
3656291 | 68251 | ATM Project | 17 | ATM_1-17 | 292312 | Bug | 92647 | Session | 63901 | 1.0 | GUI Freezes when the Card number "3" is entered. | When prompted to Insert card, if a Card number "3" is entered, the ATM still proceeds to ask for PIN; and after an arbitrary PIN is entered, the program freezes. **Function being tested:** Session **Initial state of the system:** System ask to Insert Card. **Steps to reproduce:** 1. Turn on ATM, and insert valid number of bills. 2. Insert Card 3. 3. Enter an arbitrary PIN. **Expected outcome:** The Program should return "Failure Invalid Card" **Actual outcome:** The Program still goes ahead to ask for a PIN, and when the phony PIN is entered, the program freezes. ![image][MFT 1.JPG] | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed |  |  | 319596 | OKEOGHENEMARHO OBUAREGHE | Jan. 28, 2022 01:45 |  | 319598 | Drew Burritt | Jan. 28, 2022 10:58 | 1 | 0 | Jan. 28, 2022 01:47 OKEOGHENEMARHO OBUAREGHE Fixed in V1.1
3654823 | 68251 | ATM Project | 14 | ATM_1-14 | 292312 | Bug | 92643 | Withdrawal | 63901 | 1.0 | Withdrawal wrong amount | **MFT** You choose to withdraw $60, but the ATM dispenses $100. You choose to withdraw $200, but the ATM dispenses $20. This happens incorrectly for every amount. **Function being tested** : Withdrawal **Initial State of the system** : User Withdrawal from menu and choose $60. **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 2 and enter the PIN as 1234 3. Choose Withdrawal 4. Choose $60 **Expected Outcome** ATM withdraws $60 **Actual Outcome** ATM Withdraws $100. Fixed in version 1.1 | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed |  |  | 319500 | Michael Lee | Jan. 27, 2022 15:22 |  | 319500 | Michael Lee | Jan. 27, 2022 15:23 | 0 | 0 | Jan. 27, 2022 15:23 Michael Lee Fixed in version 1.1
3654814 | 68251 | ATM Project | 13 | ATM_1-13 | 292312 | Bug | 92646 | Balance Inquiry | 63901 | 1.0 | In card 2, during balance enquiry, Money Market is shown as an Invalid Account Type although it is a valid account. | In card 2, during balance enquiry, Money Market is shown as an Invalid Account Type although it is a valid account. **Function being tested** : Balance Inquiry **Initial State of the system** : User with card 2 selects Money Market from Balance Inquiry menu. **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 2 and enter the PIN as 1234 3. Choose Balance Inquiry 4. Choose Money Market **Expected Outcome** ATM displays receipt of Money Market balance **Actual Outcome** ![image][pasted-2022.01.27-15.12.14.png] ATM displays message that it is invalid account. Fixed in version 1.1 | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed |  |  | 319500 | Michael Lee | Jan. 27, 2022 15:12 |  | 319500 | Michael Lee | Jan. 27, 2022 15:12 | 1 | 0 | Jan. 27, 2022 15:12 Michael Lee Fixed in version 1.1
3651283 | 68251 | ATM Project | 5 | ATM_1-5 | 292312 | Bug | 92646 | Balance Inquiry | 63901 | 1.0 | Savings Account Not Shown in Balance Inquiry | Savings Account Not Shown in Balance Inquiry **Function being tested** : Balance Inquiry **Initial State of the system** : User selects Balance Inquiry from main menu. **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 2 and enter the PIN as 1234 2. Choose Balance Inquiry **Expected Outcome** ATM displays account Checking, Savings and Money Market **Actual Outcome** ATM shows only Checking and Money Market ![image][pasted-2022.01.26-09.46.08.png] | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed |  |  | 319500 | Michael Lee | Jan. 26, 2022 09:49 |  | 319500 | Michael Lee | Jan. 27, 2022 15:07 | 1 | 0 | Jan. 27, 2022 15:07 Michael Lee Fixed in version 1.1
3654680 | 68251 | ATM Project | 11 | ATM_1-11 | 292312 | Bug | 92646 | Balance Inquiry | 63902 | 1.1 | Cash dispensed on balance inquiry of savings account | **MFT** Using card 1, which only has checking and savings, if savings is chosen for balance inquiry, ATM first shows unknown error, then dispenses cash ($500). Receipt shows savings balance with no change to balance when cash is dispensed. Dispensed cash is shown in log. **Function being tested** : Balance Inquiry **Initial State of the system** : System is displaying menu of account types **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 1 and enter the PIN as 42 2. Choose transaction type as Balance Inquiry 3. Choose savings account (valid account for this card) **Expected Outcome** ATM displays balance for savings account. **Actual Outcome** ATM shows balance for savings account. Cash is dispensed when checking balance. Balance does not change for any account when cash is dispensed. **ATM Log** Message: INQUIRY CARD# 1 TRANS# 1 FROM 1 NO TO NO AMOUNT Response: SUCCESS Dispensed: $500.00 ![image][Balance Inquiry Bug.jpg] | 1 | Open | 3 | Normal | [6 empty] | 319598 | Drew Burritt | Jan. 27, 2022 12:28 |  | 319598 | Drew Burritt | Jan. 27, 2022 12:30 | 1 | 0
3648535 | 68251 | ATM Project | 3 | ATM_1-3 | 292312 | Bug | 92646 | Balance Inquiry | 63901 | 1.0 | Cash dispensed on balance inquiry for invalid account type | Using card 1, which only has checking and savings, if money market is chosen for balance inquiry, ATM first shows unknown error, then dispenses cash ($500). Receipt shows savings balance with no change to balance when cash is dispensed. Dispensed cash is shown in log. **Function being tested** : Balance Inquiry **Initial State of the system** : System is displaying menu of account types **Steps to reproduce** : 1. Turn on ATM, and insert valid number of bills 2. Insert card 1 and enter the PIN as 42 2. Choose transaction type as Balance Inquiry 3. Choose account as Money Market (invalid account for this card) **Expected Outcome** ATM displays invalid account if money market is selected for card 1 **Actual Outcome** ATM shows balance for savings account on receipt when money market is selected. Cash is dispensed when checking balance. Balance does not change for any account when cash is dispensed. **ATM Log** Message: INQUIRY CARD# 1 TRANS# 1 FROM 1 NO TO NO AMOUNT Response: SUCCESS Dispensed: $500.00 ![image][Balance Inquiry Bug.jpg] | 3 | Resolved | 3 | Normal | [6 empty] | 319598 | Drew Burritt | Jan. 25, 2022 15:41 |  | 319598 | Drew Burritt | Jan. 27, 2022 12:24 | 1 | 0
3651698 | 68251 | ATM Project | 9 | ATM_1-9 | 292312 | Bug | 92645 | Transfer | 63901 | 1.0 | ATM doesnt transfer the right amount | The amount transferred by the ATM is $0.5 less than the value specified by the user. **Function being tested** : Transfer **Initial state of the system** : ON and Idle **Steps to reproduce** : 1. Insert the card 2 and enter the PIN as 1234 2. Choose transaction type as Transfer 3. Select from "Checking" and to "Money Market" 4. Enter $20.00 as the amount to transfer, and press Enter 5. Both the receipt and the log shows amount transferred as $19.50 6. The balance enquiry confirms that only $19.5 were transferred, and not $20.00 **Expected Outcome** : The ATM should have transferred $20.00 from the checking account to Money Market account. The same should have been reflected in the receipt and the logs. The balance inquiry should show total balance and available balance equal to $80.00. **Actual Outcome** : The ATM transferred only $19.50 from the checking account to Money Market account. The receipt and the logs also show that $19.50 are transferred. The balance inquiry shows the total balance and available balance equal to $80.50. ![image][Issue_Screenshot.png] | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed |  |  | 319606 | Bhavyai Gupta | Jan. 26, 2022 16:17 |  | 319606 | Bhavyai Gupta | Jan. 26, 2022 21:31 | 1 | 0